## Slide 1
Role | Influence (H/M/L) | Interest (H/M/L) | Primary Information Needs | Communication Approach
CEO | H | M | Conversion and sales data, revenue forecasts, ROAS, ROI, historical perspective | Provide overview updates with only the most essential information via email monthly and meetings quarterly
Marketing team | H | H | Engagement and conversion goals and data, campaign strategy, task assignments and deadlines | Communicate all relevant details daily via email and chat and hold weekly meetings
Project manager | M | M | Campaign progress, task assignments and deadlines, scheduling delays, budget constraints | Communicate about campaign progress bi-weekly via email and as needed and hold weekly meetings
Information technology (IT) team | M | L | Software and hardware requirements and issues, data archiving | Keep updated on requirements and issues as needed
External ad agency | M | M | Creative requirements, contractual information, scheduling, budget and payment details | Provide updates via email weekly and as needed and meetings monthly
Stakeholder Analysis

## Slide 2
Inform
Inform and respond to needs
Update
Respond to needs
high
low
high
low
Stakeholder Map
Marketing team
IT team
CEO
Project manager
External ad agency
Interest
med
Influence
med

## Slide 3
Role | Information to Be Shared | Means of Communication
CEO | ROAS ROI Revenue forecast Sales Data Historical perspective | Email a monthly dashboard Have a scheduled meeting every quarter
Marketing team | Engagement Data Conversion Data Campaign Schedule Campaign Goals Tasks and Deadlines | Have a scheduled weekly meeting Email a monthly report
Project manager | Campaign Progress Tasks and Deadlines Scheduling Delays Budget Constraints | Email bi weekly report or as needed Have a schedule weekly meeting
IT team | Data that needs to be archived Software and hardware requirements Software and hardware issues | Schedule meetings as needed
External ad agency | Creative requirements Contractual information, scheduling, budget and payment details | Schedule monthly meeting Email by weekly or as needed
Communication Plan